## QI Plan
RHNTC logo. Reproductive Health National Training Center. | Quality Improvement Plan to Increase Contraceptive Access
Use this worksheet to create a strategic quality improvement (QI) plan to increase contraceptive access at your site.
Instructions:
1. Complete the Contraceptive Access Assessment (or use other data to evaluate contraceptive access at your site).
2. Based on the data, select the relevant contraceptive access strategies and action steps for improvement at your site in columns A and B below.
3. Use the Increasing Access to Contraception Toolkit to create one or more aim statements for each relevant strategy/action step. (See the "Sample QI Plan" tab for examples.)
4. Fill in the Plan-Do-Study-Act (PDSA) information for each aim statement, referring to the "SAMPLE QI Plan" tab. You may have several tasks (column D) for each aim statement.
Contraceptive access strategy | Action step | Aim statement | PLAN Task | PLAN Person/group responsible | PLAN Deadline | PLAN Measure of completion | DO Status/progress | STUDY Data/observations | ACT Next steps
Contraceptive access strategy | Action step | What do you want to achieve and by when? (Can be the same as or a subset of the action step) | What tasks are needed to reach this aim? | Who will complete each task? | By what date will each task be done? | How will you know each task is complete? | How is the task going? | What are your takeaways? | What are your next steps?

## SAMPLE QI Plan
RHNTC logo. Reproductive Health National Training Center. | SAMPLE Quality Improvement Plan to Increase Contraceptive Access
Refer to this sample quality improvement (QI) plan as your site prepares to fill in the "QI Plan" tab.
Note: An aim statement can have several related tasks (column D). When filling out your own QI plan, consider writing "see above" for any cells that overlap across tasks.
Contraceptive access strategy | Action step | Aim statement | PLAN Task | PLAN Person/group responsible | PLAN Deadline | PLAN Measure of completion | DO Status/progress | STUDY Data/observations | ACT Next steps
Contraceptive access strategy | Action step | What do you want to achieve and by when? (Can be the same as or a subset of the action step) | What tasks are needed to reach this aim? | Who will complete each task? | By what date will each task be done? | How will you know each task is complete? | How is the task going? | What are your takeaways? | What are your next steps?
Strategy 1: Strengthen organizational commitment to contraceptive access | (Strategy 1) Assess clinic capacity to provide contraceptive access without barriers to care | Example: Clinic site will complete contraceptive access assessment and identify priority areas for improvement by November 30 | Form assessment committee with representation from each staff role | Clinic manager | August staff meeting | Committee includes at least 1 person representing each clinic role (admin, educator, front desk, MA, NP) | Committee formed | Each role represented | First meeting will be in Sept; staff need 1 hour blocked for each meeting
Strategy 1: Strengthen organizational commitment to contraceptive access | (Strategy 1) Assess clinic capacity to provide contraceptive access without barriers to care | See above | Committee completes assessment | Assessment committee | Oct 30 | All parts of assessment complete | 3 sections completed at September meeting | Staff will review following sections before Oct meeting | Staff will complete assessment at Oct meeting
Strategy 1: Strengthen organizational commitment to contraceptive access | (Strategy 1) Assess clinic capacity to provide contraceptive access without barriers to care | See above | Review completed assessment and identify priority area for improvement | Assessment committee | Nov 30 | 1-2 areas for improvement identified | Assessment committee initially identified 3 areas for improvement | Assessment committee prioritized same-day IUD access | Share assessment results and priorities with clinic staff at Dec meeting, then identify next steps
Strategy 2: Optimize clinic infrastructure and operations for contraceptive access | (Strategy 2) Develop and optimize inventory system to maintain on-site stock of a broad range of FDA-approved contraceptive methods | Example: Increase the range of contraceptive methods, including all provider-dependent FDA-approved contraceptive methods, stocked on site by Dec | Assess types of contraceptive methods currently stocked on site | Sarah | Sept 30 | # of contraceptive methods offered on site increases | Inventory of current methods stocked on site complete | Site does not have supply of ullipristal emergency contraception (EC) | Identify supplier of ullipristal EC, order, train all staff on option; track distribution x 3 months to inform next order
Strategy 2: Optimize clinic infrastructure and operations for contraceptive access | (Strategy 2) Develop and optimize inventory system to maintain on-site stock of a broad range of FDA-approved contraceptive methods | See above | Identify gaps in options and prioritize methods to make available on site | Sarah and Luisa | Oct 30 | See above | See above | See above | See above
Strategy 2: Optimize clinic infrastructure and operations for contraceptive access | (Strategy 2) Develop and optimize inventory system to maintain on-site stock of a broad range of FDA-approved contraceptive methods | Example: Track use of LARC methods for 3 months to optimize on-site stock by Dec | Review IUDs dispensed (copper and hormonal types) each month for last 3 months; track IUDs dispensed each month for next 3 months and adjust orders based on historical and current data | Luisa | Oct 30 | The monthly average # of copper and hormonal IUDs dispensed is determined | Reviewed historical data and noted use of 2-3 copper IUDs/month and 10 hormonal IUDs/month; clinic has run out of hormonal IUD supply twice in last 6 months | When clinic ran out of hormonal IUD stock, 2 clients had to reschedule, which postponed the placement of their preferred method; current copper IUD stock of 10, which will supply clinic for 2-3 months | Copper IUDs: will reorder when stock is at 3 IUDs; will change hormonal IUD orders and reorder when stock is at 5 IUDs
Strategy 3: Routinely screen for reproductive desires and provide client-centered contraceptive counseling | (Strategy 3) Use an evidence-based, client-centered approach to screening for reproductive desires (e.g., PATH, OKQ, SINC, RHSSQ) | Example: Increase the % of client visits with documentation of SINC screening completed from 10% to 50% by June | Share documentation on current level of SINC screening with staff along with the identified goal and timeline | Jasmine | Mar 30 | % of client visits with documentation of SINC screening will increase | Staff were surprised by low level of documentation | Staff are motivated to increase documentation of SINC and asked for progress updates | Bi-weekly progress of SINC documentation added to huddle board for staff to view/review
Strategy 3: Routinely screen for reproductive desires and provide client-centered contraceptive counseling | (Strategy 3) Use an evidence-based, client-centered approach to screening for reproductive desires (e.g., PATH, OKQ, SINC, RHSSQ) | See above | Have staff identify where in chart they currently document SINC | Jasmine | Mar 30 | See above | Some providers are remembering to document and some aren't; maybe a change to the EMR template would help | There was a range of 10% to 50% visits with documented birth control method | Make change in EMR so providers cannot move to final screen without filling out response to SINC
Strategy 4: Establish systems to ensure timely access to a client's desired contraceptive method | (Strategy 4) Put systems in place for same-visit (“quick start”) initiation for a broad range of contraceptive methods, including intrauterine devices (IUDs) and implants | EXAMPLE: Among women who receive a LARC, increase the % of women who receive their contraceptive method on day of initial visit from 0% to 33% by May 31 | Prepare LARC method-specific packets that include educational and consent forms, instruments, and all needed equipment in a bag that staff can grab and use if client requests a LARC method that day | Marcel | First week of April | Of women receiving a LARC, # who received it the same day they first requested it | The first day, there were some items missing in packets, but we identified the missing items and added them to all packets | Once the packets were complete, this helped reduce the burden of time for insertion of a LARC | We need to continue to prepare packets weekly (or more, if needed) and may need to order more tenaculums to make up all the packets
Strategy 4: Establish systems to ensure timely access to a client's desired contraceptive method | (Strategy 4) Put systems in place for same-visit (“quick start”) initiation for a broad range of contraceptive methods, including intrauterine devices (IUDs) and implants | See above | When scheduling a visit, extend visit time by 15 minutes for clients indicating desire for IUD at time of scheduling | Joanne | Beginning first week of April | See above | The first week, there were a few visits that did not get the extra 15 minutes tacked on | Front office staff and MAs scheduling visits were reminded of the guideline, and all written guidance for visit time was updated | Periodic reminders to staff scheduling clients and all new staff will be added to staff meetings
Strategy 5: Implement strong front desk staff practices to reduce financial barriers for clients | (Strategy 5) Correctly apply your agency’s sliding fee scale to determine client fees for services based on their family size, income, and insurance coverage | EXAMPLE: Audit 10% of charts each month x 2 months to review application of agency sliding fee schedule and identify gaps | Create system for identifying charts to audit, and ensure charts reviewed capture all front desk/intake staff | Lucy and Jose | 2025-05-30 | # of charts and audit schedule identified (e.g. every day, week, or month) | Due to front desk capacity and staffing, decided 10% or no more than 10 charts will be audited each week | After first week of audits, staff developed a procedure for performing audits, which has reduced the time needed and increased consistency of audits; staff report performing audits has improved how they apply the sliding fee scale | Based on a staff recommendation, will rotate auditing task among staff every 3-6 months
Strategy 5: Implement strong front desk staff practices to reduce financial barriers for clients | (Strategy 5) Correctly apply your agency’s sliding fee scale to determine client fees for services based on their family size, income, and insurance coverage | See above | ~10% of charts from prior week will be reviewed weekly; this is approximately 10 charts per week | Lucy and Jose | 2025-05-30 | ~10 charts audited per week with documentation on whether each chart correctly or incorrectly applies the sliding fee scale | 3 weeks into process and audits have been happening each week | On review of audit data, about 50% of charts did not have sliding fee scale applied correctly due to some staff using old fee schedule | Update all front desk resources with new sliding fee schedule; continue weekly audits and address emerging trends/gaps with staff

## Performance Measure Trckr
RHNTC logo. Reproductive Health National Training Center. | Performance Measure Tracker
Performance measures can help you track the impact of action steps you take to enhance access to contraceptive care and support quality improvement.
Use this worksheet to document your site's contraceptive access performance measures and evaluate contraceptive access at your site over time.
As you select performance measures, keep in mind:
- It is important to include performance measures that gauge multiple aspects of care, inclding potential barriers to access, quality, workflow improvements, and clients' care experiences.
- Examples of validated measures you can use include UCSF's Person-Centered Contraceptive Counseling Measure1, OPA's Contraceptive Care Measures2, and those described in the "Related Contraceptive Care Measures" section of OPA's page.
- Some performance measures (e.g., OPA contraceptive care measures) are not intended to have set quotas. Quotas can incentivize providers to prioritize certain methods, like LARCs, thereby undermining client autonomy and client-cenetered care.
- To learn more about how to use performance measures, go to OPA's Contracetpvice Care Measures page and scroll down to the "How to Use the Measures" section.
1https://pcccmeasure.ucsf.edu/
2https://opa.hhs.gov/research-evaluation/title-x-services-research/contraceptive-care-measures
Instructions:
1. Duplicate this tab as many times as needed to create a unique tab for each performance measure your site wants to track.
2. On each tab, add the performance measure (column B) and related aim statement (column A), if applicable.
3. The default unit of measure is whole numbers. To change it, highlight cells C19-N19, right click, choose "Format cells," and select the desired unit (e.g., percentage with 2 decimal places).
3. Enter performance data for each measure on an ongoing basis (columns C through N). Once you enter data, the average (column O) will appear automatically. Data will appear in the chart when at aleast two months' data is entered.
4. Track the average and/or trend over time and implement quality improvement activities for any measures with concerning data, using the "QI Plan" tab and toolkit as needed.
All data entered into the following table is also displayed in a dynamically updated line graph.
Aim statement | Performance measure | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Average
ENTER AIM STATEMENT | ENTER PERFORMANCE MEASURE | [12 empty] | TBD

## SAMPLE Performance Measure Trck
RHNTC logo. Reproductive Health National Training Center. | SAMPLE Performance Measure Tracker
Refer to this sample performance measure tracker as your site prepares to fill in (and duplicate) the "Performance Measure Tracker" tab.
All data entered into the following table is also displayed in a dynamically updated line graph.
Aim statement | Performance measure | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Average
EXAMPLE: Among women who receive a LARC, increase the # of women who receive their contraceptive method on day of initial visit from 0 to 15 by May 31 | EXAMPLE: # of clients who received a LARC method on the same day they first requested it | 3 | 4 | 6 | 5 | 5 | 8 | 9 | 10 | 13 | 12 | 15 | 14 | 8.6667

## Funding Statement
This toolkit was supported by the Office of Population Affairs (Grant FPTPA006030). The views expressed do not necessarily reflect the official policies of the Department of Health and Human Services; nor does mention of trade names, commercial practices, or organizations imply endorsement by the U.S. Government.

## DropdownsRanges (hidden)
StrategyOneActionSteps | StrategyTwoActionSteps | StrategyThreeActionSteps | StrategyFourActionSteps | StrategyFiveActionSteps
Assess clinic capacity to provide contraceptive access without barriers to care. | Clearly and accurately promote contraceptive services through both mass communication (e.g., website, social media) and communication with individual clients (e.g., at check-in, over the phone, through the portal). | Use an evidence-based, client-centered approach to screening for reproductive desires (e.g., PATH, OKQ, SINC, RHSSQ). | Put systems in place for same-visit (“quick start”) initiation for a broad range of contraceptive methods, including intrauterine devices (IUDs) and implants. (If unable to provide the client’s contraceptive method of choice on the same day they request it, offer a bridge method of contraception.) | Develop an income verification policy and monitor front desk practices in carrying it out.
Create and communicate an organizational vision for contraceptive access that emphasizes client-centered care (focused on the client’s needs, values, and preferences) in line with Title X expectations. | Participate in (and have a policy for) the 340B Drug Pricing Program, to obtain lower-cost contraceptives and supplies. | Provide information on a broad range of FDA-approved contraceptive methods, including methods not provided on site. | Train clinicians on insertion and removal of long-acting reversible contraceptive (LARC) methods, such as IUDs and implants. | Train all front desk staff on income verification, sliding fee scales, and confidential billing.
Have a policy and procedures describing the process for ensuring quality service delivery for all consistent with nationally recognized standards of care. | Develop and optimize inventory systems to maintain on-site stocking of a broad range of FDA-approved contraceptive methods. | Provide client-centered contraceptive counseling to help each client select a contraceptive method that aligns with their needs, values, and preferences. | Offer an extended contraceptive supply (a 6 to 12 month supply of combined hormonal methods, like the pill, patch, or ring) at the time of the visit. | Prepare front desk staff to inform clients about self-pay, sliding fee schedules, and insurance enrollment options, to ensure clients have access to services without delay and regardless of ability to pay.
Have a policy and procedures describing the process for ensuring that individuals are not pressured or coerced to receive contraceptive services or to use or not use any particular contraceptive method. | Train and support staff responsible for billing and coding on accurate coding and how to promptly manage denials of reimbursement for contraceptive services. | Recognize and support clients interested in using contraceptive methods for reasons other than contraception (e.g., STI/HIV prevention, menstrual regulation, acne). | Provide information and counseling on self-care contraceptive options (DMPA-SC, over-the-counter progestin-only pills, fertility awareness-based methods) and information, as needed. | Correctly apply your agency’s sliding fee scale to determine client fees for services based on their family size, income, and insurance coverage.
Put systems in place to regularly gather client feedback on access to and experience with contraceptive services at your site. | Offer flexible clinic hours, including evenings and weekends. | Cultivate an awareness of how staff backgrounds and experiences influence the information they share, the language they use, and how they counsel clients. | Offer emergency contraception (EC) to all clients, as appropriate, including offering an advance supply. | Screen for confidential billing needs by asking all clients if they have concerns with documentation being sent to their home.
Put systems in place to evaluate contraceptive access and implement quality improvement activities, including collecting, reporting, and using data. | Other | Provide instructions and ensure client understanding about how to use their selected method correctly and consistently, including how to access it, optimize use, discontinue or switch methods, manage side effects, and anticipate problems (e.g., late dosing). | Offer contraceptive services via telehealth, as appropriate. The following contraceptive services are suitable for telehealth provision: | Other
Other |  | Train staff on contraceptive methods and method-specific eligibility criteria. | Build a strong referral network for contraceptive methods not provided on site.
|  | Train staff on client-centered contraceptive counseling approaches and skills. | Optimize clinic flexibility and efficiency:
|  | Train staff on contraceptive method misinformation and myths and how to counsel clients. | Other
Other
Toolkit Strategies
Strategy 1: Strengthen organizational commitment to contraceptive access
Strategy 2: Optimize clinic infrastructure and operations for contraceptive access
Strategy 3: Routinely screen for reproductive desires and provide client-centered contraceptive counseling
Strategy 4: Establish systems to ensure timely access to a client's desired contraceptive method
Strategy 5: Implement strong front desk staff practices to reduce financial barriers for clients
StrategyMap[Strategy] | StrategyMap[RangeName]
Strategy 1: Strengthen organizational commitment to contraceptive access | StrategyOneActionSteps
Strategy 2: Optimize clinic infrastructure and operations for contraceptive access | StrategyTwoActionSteps
Strategy 3: Routinely screen for reproductive desires and provide client-centered contraceptive counseling | StrategyThreeActionSteps
Strategy 4: Establish systems to ensure timely access to a client's desired contraceptive method | StrategyFourActionSteps
Strategy 5: Implement strong front desk staff practices to reduce financial barriers for clients | StrategyFiveActionSteps
_BlankList
Error: Select strategy first