## Improvement Plan
Reproductive Health National Training Center (RHNTC). Patient Experience Improvement Plan. Table starts at A 4 and is organised into four sections: Clinical Systems (A5); Patient Interactions (A11); Clinical Environment (A17); Staff Experience and Engagement (A23).
Patient Experience Improvement Plan
Use this improvement plan to organize and track patient experience improvement efforts in your family planning clinic. Add new rows as needed.
Improvement Goal | Improvement Activity | Who is Responsible | How You Will Evaluate Success of Improvement Activity | Deadline for Evaluating Improvement Activity | Results and Next Steps (fill in when activity completed and evaluated)
CLINIC SYSTEMS
Example: Expedite patient check-in process. | Review patient check-in paperwork and identify opportunities to streamline it. | Jacob (Nurse) | Patient time filling out paperwork, gathered through observation. | April 10th | Combined three intake forms into one streamlined form. Average time patients spend filling out paperwork decreased from 12 minutes to 4 minutes.
PATIENT INTERACTIONS
Example: Ensure all patients feel welcome at the clinic. | All staff complete the Skills for Improving Family Planning Visits: Staff Meeting Package to practice how to make welcoming statements. | Rita (Clinic Manager) will organize staff meeting; all staff will attend: Jacob (Nurse), Marta (Front Desk), and Tre (Nurse Practioner) | Patient satisfaction surveys | March 1st | In March, patient satisfaction surveys showed an increase in positive responses (from 85% to 95%) on the question, "Did you receive a friendly welcome?".
CLINIC ENVIRONMENT
Example: Protect patient confidentiality. | Put a white noise machine in the hallway. | Rita (Clinic Manager) will make purchase; Marta (Front Desk) will install and test | Test to make sure we can't hear voices from the hallway in the exam rooms and vice versa. | March 15th | Test successful—white noise machine blocks carrying of voices.
STAFF EXPERIENCE AND ENGAGEMENT
Example: Give staff regular opportunities to get support. | Institute twice daily team huddles. | Rita (Clinic Manager) | After one week, ask staff to fill out a brief anonymous survey sharing what is working and what could be improved. | March 9th | Staff appreciate huddling but find twice daily huddles (morning and afternoon) to be disruptive and time-consuming. Planning to try just one morning huddle and will reevaluate after one week of new approach.